## Tasks (hidden)
Description | Application | Complete date
Turn off Display power management features and remove all printers from Dispatch1 profile | CAD
Modify DISPATCH1 profile to disable Accessability options. | CAD
Get copies of CAD client interface registry entries from all agencies | CAD
Develop process to get CLETS response info out to CD for archive retrieval. | CAD
Develop ping command files for dispatch workstations | CAD
Create CAD user accounts for Kevin Lacefield and Matthew Lawton | CAD
Create ARCHIVE1 account for reopening Archive CAD records. | CAD
Update LEADS server sonoma.map file while LEADS down | LEADS | 2003-10-02
Test 1 Employee with 2 user accounts SD/WI | LEADS
Setup analyze script as scheduled job | LEADS
Set duplicate ID notification (DL-SSN) in Tools-Agency config-Names | LEADS
Schedule NameAge update run monthly | LEADS
Run script to replace '&" in Names with 'and" | LEADS
Run Analyze | LEADS
Review CFS/Incident/Accident for each agency and define bad/dupe records | LEADS
Perform Cold backup while LEADS down | LEADS | 2003-07-03
Pack files while LEADS down. | LEADS
Modify Affidadavid form to include Offense Code | LEADS
Identify records with bad case date, bad DOB, bad number format. | LEADS
Identify method to clear login records | LEADS
Identify broken link records - CFS/Incident/Involvement/Arrest | LEADS
Get info from David on creating 'banner' on report pages that contains user info for who printed the report | LEADS
Follow up on CO Alarm Report blank - No Alarm register records | LEADS
Determine method to deal with "Unknown" registered owner/Name records. Use License. David says license plate is common. | LEADS
Define Global alert codes | LEADS
Define dispo codes for false alarm billing from CAD and use in Alarm Module | LEADS
Create troubleshooting documentation | LEADS
Add Muni code translations and zips to city codes | LEADS
Install MARS at CO, CL, JC, SO | MARS
Update perms for users on MDC system files | MDT
Update Mobile Config with Manual entry for all but Arrest for all Agencies | MDT
Update MDC dispo codes | MDT
Remove Games executables | MDT
Perform load model testing with modified AFR counts. (10/hr per 100 veh. 350k/hr. 7 AFR transactions not 1. | MDT
Make Notes field Read Only on AFR image and Training server | MDT
Identify method to allow short term account access to account with install perm | MDT
Document AFR load procedure | MDT
Copy SDLOGO.JPG to Law images | MDT
Stop IIS and delete the netviewer log file | NetViewer
Define method to address verify for NetViewer users without creating advised event | NetViewer
Set Oracle INTERNAL password using DBA Studio and SYS account | Oracle
Install AFR and I/Mobile Law at all Franklin workstations. | Training
Develop method to run AFR, LEADS and Mobile Training on same W/S for Franklin | Training
Purchase SnagIt | Buy | 2003-09-03
Purchase Oraxcel | Buy

## Requests-Issues (MPS)
Requests/Issues Tracking
Pri | ID | Date Filed | Source | Initials | Request/Issue | Type | App 1 | App 2 | Priority | Status | Group Assigned | CENCOM Disposition | CENCOM Comments | Cloud5 Disposition | Cloud5 Comments | Assigned to | Closed By | Closed Date | SR | HxGN Disposition | HxGN Comments
| 44 |  | CENCOM |  | F7 - sends Dispatch Arrive instead of Enroute | Other | Interface | MDT/MPS |  | Open | CENCOM |  |  | Awaiting CENCOM | Unable to reproduce
| 46 |  | CENCOM |  | MPS LAW: Add Case # from My Dispatch is not saving their users' choice and needs to. They have to choose their agency every time they assign a case number and its leading to many mistakes | Other | Interface | MDT/MPS | P3 | Open |  |  | Reopened: additional information received | Closed | Closed, non issue
| 52 |  | CENCOM |  | When a MCT user clicks Available MCT it sets them to AM instead of new AV status |  |  | MDT/MPS | P3 | WAD (Closed) | CENCOM |  |  | Awaiting CENCOM | Per Stephanie Trueblood this is not an issue at this time.
| 66 | 2016-07-20 | CENCOM |  | Unable to open prefire plans in MPS. Getting "Page cant be displayed" error. Prefire does exist on MCT in correct location and link in cad is correct path. Unable to pull up manually from LOI search as well |  | Other | MDT/MPS | P3 | Open
| 67 | 2016-07-21 | MCTUser | TLU | On the MAP when you click on track Unit, the map stays in full Kitsap County Mode view instead of zooming in on where the patrol vehicle is. User has to press rotate map to get it to zoom in, but they dont like to use Rotate Map as the GPS causes it to twitch (rotating back and forth) when sitting still. Would like the map to zoom into the unit when Track Unit is checked | Config | Other | MDT/MPS | P3 | Open
| 73 | 2016-03-30 | CENCOM | TLU | FIRE MPS: Need to modify event types to match what they are allowed to use >>> As of 060316: Missing BOLO & TESTF. TESTF fixed 07/12/16 | Config | Interface | MDT/MPS | P3 | Open
| 74 | 2016-03-31 | CENCOM | TLU | FIRE MPS: Unit & Event Shift Activities on Dashboard: Check if need to change to a smaller time frame like 24hours, since Fire doesn’t sign off for days or weeks at a time | Config | Interface | MDT/MPS | P3 | Open
| 75 | 2016-05-17 | CENCOM | TLU | FIRE & LAW MPS: Not all common names are verifying and entering the address. Examples working: @Cencom, @Jail, @Coroners. NOT Working: @Burger King, @Mcdonalds, @Kitsap County. This is an issue in all location fields, including Map - Command - Find Address. It wont verify common names with more than one choice so you cant display it on the map either | Config | Interface | MDT/MPS | P2 | Open
| 76 | 2016-03-28 | CENCOM | TLU | MPS: Need to modify ADVANCED MENUS; Copy used items to other menus and hide items we don’t use at all from Advanced | Config | Interface | MDT/MPS | P4 | Open |  |  | Cencom Reviewing
| 77 | 2016-03-29 | CENCOM | TLU | FIRE MPS: On Map - Information Tab - Show Lat/Long <<< Is displaying Lat&Long incorrectly | Config | Interface | MDT/MPS | P4 | Open
| 78 | 2016-03-29 | CENCOM | TLU | FIRE & LAW MPS: Modify the groups to remove unused, such as alsd, CADLOG, CENCOM, DISPATCH, EQUIPAGE, FPRINT, ITPAGERS, SWAT | Config | Interface | MDT/MPS | P4 | Open
| 79 | 2016-03-29 | CENCOM | TLU | FIRE & LAW MPS: Map - Map Pickers: Common names not showing correct address in left side compared to actual event address | Config | Interface | MDT/MPS | P4 | Open
| 80 | 2016-03-31 | CENCOM | TLU | FIRE & LAW MPS: Road Retrictions, Cencom reviewing if mobiles will use or not. If not we will need to hide the functionality from mobiles | Config | Interface | MDT/MPS | P4 | Open |  |  | Cencom Reviewing
| 81 | 2016-03-31 | CENCOM | TLU | MPS: Transport Hospital Tab: make page of one touch buttons. Build all locations then Regenerate options files | Config | Interface | MDT/MPS | P4 | Open
| 82 | 2016-07-26 | MCTUser | TLU | LAW MPS: Dispatcher's not easily able to tell if a unit is MCT equipped or no, or has AVL Location (Sprague) | Training | Interface | MDT/MPS | P4 | Open |  |  | Cencom Reviewing
| 83 | 2016-07-26 | MCTUser | TLU | LAW MPS: While typing into a NCIC form, the event notification popup took focus away from the data form and brought the user to the event. Using back button only brings you back to blank form, all data typed lost. This doesn’t happen with event updates, just with the dispatch popup. Confirmed TLU | Config | Interface | MDT/MPS | P2 | Open
| 84 | 2016-07-26 | MCTUser | TLU | LAW MPS: Event Popup changing unit status timer during a traffic stop is problematic. | Config | Interface | MDT/MPS | P3 | Open |  |  | When dispatched to a traffic stop (whether by dispatch or MPS user) the MPS user receives the popup and their status changes, by design, same as IMobile.
| 90 | 2016-08-01 | MCTUser | TLU | MPS: Update button lighting up for every gps transmission while dispatched to an event. This was suppposed to be turned off. Only happens while dispatched to an event. | Config | Interface | MDT/MPS | P3 | Open |  |  | Bmyers reported
| 91 | 2016-08-01 | MCTUser | TLU | MPS: When sending messages to multiple recipients the messages don’t always get received by everyone (even though they are logged in at the time). | Defect | Interface | MDT/MPS | P3 | Open |  |  | Bmyers reported
| 92 | 2016-08-01 | MCTUser | TLU | MPS: Fetch Unread doesn’t seem to be checking every time you log into MPS, as it did before. May be related to item#91. Have received a unread message notification and find that the message was from a week or so ago, when the unit was logged in and should have recieved it. | Defect | Interface | MDT/MPS | P3 | Open |  |  | Bmyers reported
| 93 | 2016-08-01 | MCTUser | TLU | MPS: Is it possible to have a filter just for the Patrol Dashboard? KCSO requesting as they have multiple dgroups and using this with all selected doesn’t show what they need to see. | Config | Interface | MDT/MPS | P3 | Open |  |  | Bmyers reported
| 94 | 2016-08-01 | MCTUser | TLU | MPS: Request a page of buttons for agencies/dgroups for Pending events reports (static reports) as they had in Imobile. The current method of retrieving these reports is very cumbersome and not workable | Config | Interface | MDT/MPS | P2 | Open
| 95 | 2016-08-01 | MCTUser | TLU | MPS: Requesting to add the agency and dgroup columns to the Unit & Event Monitors, in order to facilitate sorting | Config | Interface | MDT/MPS | P3 | Open
| 96 | 2016-08-01 | MCTUser | TLU | MPS: Unit Summary Reports, if you click on a unit for an agency other then your own the report comes back as "No online unit called J121"….. But does come back for your own unit. Need this fixed to allow all agencies to see eachothers unit information | Config | Interface | MDT/MPS | P3 | Open |  |  | Bmyers reported
| 97 | 2016-08-01 | MCTUser | TLU | MPS: Unit and Event Monitors, can we add a secondary sort option such as adding the Agency column and being able to sort by agency then dispatch group | Config | Interface | MDT/MPS | P3 | Open |  |  | Bmyers reported
| 98 | 2016-08-01 | MCTUser | TLU | MPS: My Shift Activities buttons default to last time your unit signed on. When KCSO units change their unit (from a South unit C103 to a North unit N143) within the same shift they can no longer see the history with these buttons before they signed in with the new Unit. Can we make this report look for their Personnel of 103 instead of unit C103 or N103?? OR ? | Config | Interface | MDT/MPS | P3 | Open |  |  | Bmyers reported
| 99 | 2016-08-01 | MCTUser | TLU | MPS: Event Search Report, only allowing user to select from the list of events that they can create field events for. They need ability to search for ALL event types, law or fire as well. | Config | Interface | MDT/MPS | P3 | Open
| 100 | 2016-08-01 | MCTUser | TLU | MPS: Event Searches arent allowing you to use the wild card % as they did before | Config | Interface | MDT/MPS | P3 | Open
| 101 | 2016-08-01 | MCTUser | TLU | MPS: Unit Summary - Need to list the agencies and dgroups alphabetically by their acronym then description, for example: BPD - Bremerton Police Department CKFR - Central Kitsap Fire & Rescue | Config | Interface | MDT/MPS | P3 | Open
| 102 | 2016-08-01 | MCTUser | TLU | MPS: Need to check the update rates for AVL in cad, based on status. May not be correct. Some not getting updated frequent enough, some more often then needed. | Config | Interface | MDT/MPS | P3 | Open
| 106 | 2016-07-23 | CENCOM | TLU | MPS: When a unit clears an event the dispatch report goes away, unlike it did in Imobile. Would like cleared events to still be accessible without having to perform a query | Config | Interface | MDT/MPS | P3 | Open |  |  | Would like to address during Reassessment
| 107 | 2016-07-23 | CENCOM | TLU | MPS: Request a page of buttons for agencies/dgroups for Unit Summary reports (static reports) as they had in Imobile. The current method of retrieving these reports is very cumbersome and not workable having to use drop downs | Config | Interface | MDT/MPS | P3 | Open
| 108 | 2016-07-12 | CENCOM | TLU | MPS LAW: Data attached to events is very unreadable in MPS. Needs formatting/spacing. | Config | Interface | MDT/MPS | P2 | SR |  |  | SR1-1348300001
| 109 | 2016-07-23 | CENCOM | TLU | MPS LAW: Is it possible to increase the font size on the NCIC returns? It would make it much easier to read (WO#37125) | Config | Interface | MDT/MPS | P3 | Open
| 110 | 2016-07-12 | CENCOM | TLU | MPS LAW: The vehicle form needs additional spacing/formatting of the form (WO#36711) | Config | Interface | MDT/MPS | P3 | Open
| 111 | 2016-07-23 | CENCOM | TLU | MPS LAW: Free form needs spacing/formatting to see all comments below and the drop down needs to default to WACIC | Config | Interface | MDT/MPS | P3 | Open |  |  | SR
| 112 | 2016-07-23 | CENCOM | TLU | MPS: MY Menu limited to certain functions. Is it possible to add more functions to this? | Config | Interface | MDT/MPS | P4 | Open
| 113 | 2016-07-23 | CENCOM | TLU | MPS LAW: Would like to add the SIGNON FORM to the Home- Favorites page. Sometimes users navigate away from the signon page and there is no easy way to get back to it. | Config | Interface | MDT/MPS | P4 | Open
| 114 | 2016-07-23 | CENCOM | TLU | MPS LAW: Request to add the ADR form to the NCIC menu | Config | Interface | MDT/MPS | P4 | Open
| 118 | 2016-08-09 | CENCOM | TLU | MPS LAW: Have a second reported instance where the patrol dashboard had too many events, not taking into account the filters. Had to close and reopen MPS to fix | Defect | Interface | MDT/MPS | P3 | Open |  |  | WO#37166
| 120 | 2016-08-11 | CENCOM | tlu | MPS: When a unit clears an event, sometimes the Patrol dashboard still shows the event (on their screen only) and the Unit Monitor still shows the event id next to their unit (on their screen only). Closing and reopening MPS fixes this, however we need this fixed as its causign confusion as to whether or not the unit has been cleared from an event. UPDATE 08/16/16: This is happening more frequently then initially thought and not just for the unit that was on the call. Others can see closed calls that they werent dispatched to on the patrol dashboard | Defect | Interface | MDT/MPS | P2 | Open
| 122 | 2016-08-17 | CENCOM | TLU | MPS: When an MPS client loses connectivity to the server yet is still receiving gps coordinates it is receiving an error message "GPS COMMENT BACK DATED COMMAND TOO OLD, DISCARDING" for every single gps coordinate received during that time frame. And for every one of these messages the blue notification bar pops up. When a unit has been in this state for hours or even most of the shift its locking up the MPS client. You have to kill MPS and reopen it and it takes a few minutes for it to reopen. | Config | Interface | MDT/MPS | P2 | Open
| 123 | 2016-08-17 | CENCOM | TLU | MPS: CENCOM Custom statuses not displaying on the MPS Map. Only show a red dot. Unavailable (UA) is one of them. | Config | Interface | MDT/MPS | P3 | Open
| 124 | 2016-08-17 | CENCOM | TLU | MPS FIRE: Available With Disposition. The button at the top goes to the correct page of buttons to use. However if you go to the form by Home - Status Menu- it isnt pointing to the same page of buttons. Its using the drop down lists. Need to point to the page same as the button on top does. | Config | Interface | MDT/MPS | P3 | Open
| 125 | 2016-08-19 | CENCOM | TLU | Patrol Dashboard: Can we set geographic barriers so its not showing events across the water?? Its not helping to find closest call via driving | Config | Interface | MDT/MPS | P3 | Open
| 126 | 2016-09-06 | KCSO | TLU | Map: the white boarder around the map is too bright when in night mode. Needs to be changed to a more muted color like the rest of the application is in night mode | Config | Interface | MDT/MPS | P3 | Open
| 127 | 2016-09-06 | KCSO | TLU | MPS: Would like a Save View type of functionality added back to the map (similar to what was in Imobile) | Config | Interface | MDT/MPS | P3 | Open |  |  | Previously told this is not possible in MPS. May need to file a CR with IPS
| 128 | 2016-09-06 | KCSO | TLU | MPS: Can we adjust the zoom levels of the map to take less drastic steps, so more zoom levels | Config | Interface | MDT/MPS | P3 | Open
| 129 | 2016-09-06 | KCSO | TLU | MPS: When on Event Viewer and you click on Show Map, Is it possible to move the map tool buttoms that are currently in the top right to the left so that you can see more of the map? Or possibly hide these? | Config | Interface | MDT/MPS | P3 | Open
| 130 | 2016-09-06 | KCSO | TLU | MPS: Event tags on the map are very long an unintelligent. Is it possible to make these popups to click on and see the event information such as the event number and type? Or at the minimum shorten the event tag to just the last 3-4 characters? | Config | Interface | MDT/MPS | P3 | Open
| 131 | 2016-09-06 | KCSO | TLU | MPS: Is there a "Reset" function to reset MPS to default views similar to when you first log on? We had "Restore View" in Imobile which was helpful when someone dragged a window where it didn’t belong. In MPS we had a user click on the map tabs and somehow make them dissappear. He had to close and reopen MPS to get the tabs back | Config | Interface | MDT/MPS | P3 | Open
| 132 | 2016-09-12 | CENCOM | TLU | MPS: Route is not automatically clearing from MPS when cleared from an event. Had to manaully go to the Route tab and click on the Clear Route button to clear it. This should happen automatically when a unit is cleared from an event | Config | Interface | MDT/MPS | P3 | Open
| 133 | 2016-09-06 | KCSO | TLU | MPS LAW: The "subject) of the data returns needs to be more descriptive of what was run. It is impossible to scroll through all of the data returns during your shift and find the one you need. The help file shows examples of better labeling on these returns. This is becoming a big issue as users are re running their data because they cant find it in the inbox | Config | Interface | MDT/MPS | P3 | Open
| 134 | 2016-09-06 | KCSO | TLU | MPS: Ocassionally the Units & Events Monitors will stop refreshing. You have to close and Reopen MPS to get them to refresh | Config | Interface | MDT/MPS | P3 | Open
| 135 | 2016-09-06 | KCSO | TLU | MPS: Want ability to print events (whether dispatched to in My Dispatches or from Event Search Results in the My Inbox). All other messages In the My NCIC and My Inbox have the print option. | Config | Interface | MDT/MPS | P3 | Open
| 136 | 2016-09-06 | KCSO | TLU | MPS: Request the buttons for notifications on the notifications bar be larger. They are hard to press on while in the car. | Config | Interface | MDT/MPS | P3 | Open
| 137 | 2016-09-06 | KCSO | TLU | MPS LAW: Would like the My Dispatches to keep events you have cleared from and give ability to delete when needed. Currently it only has the one event that you are currently dispatched to. | Config | Interface | MDT/MPS | P3 | Open
| 138 | 2016-09-06 | KCSO | TLU | MPS: would like to address the night colors of MPS, specifically the bribht green on the text of the patrol dashboard is too bright at night. | Config | Interface | MDT/MPS | P3 | Open
| 139 | 2016-09-06 | KCSO | TLU | MPS: Request to add Ctrl U function to center map on your unit. And Ctrl E function to center map on your event. Or make buttons for this. | Config | Interface | MDT/MPS | P3 | Open
| 140 | 2016-09-06 | KCSO | TLU | MPS: Unable to click on map to find a block number or street range as we did before in IMObile. Have to contact Dispatcher for that information. “Maps/address function does not show numbers so on tickets have to get block number from CENCOM which ties up radio time. When looking up address no pointer to show it.” | Config | Interface | MDT/MPS | P3 | Open
| 141 | 2016-09-06 | SPD | TLU | MPS: Can we adjust the configurations for Unit History pins to keep them much longer, prerably for the unit's entire shift | Config | Interface | MDT/MPS | P3 | Open
| 142 | 2016-05-18 | KAC | TLU | MPS LAW: For the Transport button "Humane Society" need to change the common name sent to "@Humane Society". Its currently sending "@Humane Society Shelter" which doesn’t verify. | Config | Interface | MDT/MPS | P3 | Open
| 145 | 2016-03-29 | CENCOM | TLU | MPS LAW: Remove KAR from Filter Events - DGRoup | Config | Interface | MDT/MPS | P3 | Open
| 146 | 2016-05-18 | CENCOM | TLU | MPS: Person in Suppl info, On load of form needs to default to start on the Name field. Currently defaulting to OLN field | Config | Interface | MDT/MPS | P3 | Open
| 147 | 2016-03-29 | CENCOM | TLU | MPS: Ensure ability to put themselves DA (Dispatch Assigned) is not available until CENCOM reviews this and if units will need to do this or not. Can address at Reassessment | Config | Interface | MDT/MPS | P3 | Open
| 148 | 2016-05-18 | CENCOM | TLU | MPS: When multiple events (DA) are assigned to a unit there are previous and next buttons next to Show List button. It pushes the other buttons down a line and makes the event information get covered by the tabs. This was to be addressed by cutover | Config | Interface | MDT/MPS | P3 | Open
| 149 | 2016-05-18 | CENCOM | TLU | MPS LAW: Traffic Stop on Patrol Dashboard - Ok for WA. For out of state plates it requires additional fields (Lilcense year and License type). So we need to either add these two fields or default the state to WA only and block users from changing it. This was to be assessed by cutover | Config | Interface | MDT/MPS | P3 | Open
| 150 | 2016-09-14 | CENCOM | TLU | Informer responses that are attached by an MDT user (specifically the DOL Photos) arent labeled intelligently enough in the Remarks column of te LOI Window in CAD. All other returns are prefaced with 9905:WACIC-CC14 in remarks column showing the operator and terminal that ran the inquiry. The DOL photo just shows "DOL Photo Response". The dispatcher has no way of deciphering who ran the inquiry. | Config | Interface | MDT/MPS | P3 | Open
| 151 | 2016-09-12 | CENCOM | TLU | MPS: Some units started receiving duplicate cad messages and data returns staring around approximately 09/01/16. See work order#37418 | Config | Interface | MDT/MPS | P3 | Open
| 152 | 152 | 2016-09-19 | SKFR | TLU | MPS: would like an option for a full screen map (on the Getacs the map displays too small) | Config | Interface | MDT/MPS | P3 | Open
| 153 | 153 | 2016-09-19 | SKFR | TLU | MPS: The map does not zoom in or out when you use pinch zoom on the Getacs, needs to | Config | Interface | MDT/MPS | P3 | Open
Note on F32: Terese Ungren: From: John Sprague Sent: Monday, August 01, 2016 17:29 To: Terese Ungren <TUngren@co.kitsap.wa.us> Subject: AVL Update Rates Terese, I am curious about the update rates for AVL. A few people have commented to me about how their position has been getting updated infrequently. One of the sergeants was telling me how he sometimes gets to the Silverdale office and notices that AVL still shows him in Gorst or someplace that he passed quite a while ago. On the other hand, some others seem to be about the same as usually. That having been said, I noticed that this afternoon I was up at the fairgrounds and showed on AVL as I signed-out at a detail. Then I cleared and went to unavailable status, parked on Nels Nelson Road for quite a while during some phone calls and email, then drove to buy a snack and get into my office. When I logged onto NetViewer in the office, I notice that AVL still showed me as being at the part of the fairgrounds that I had been at much earlier. Perhaps an hour or so had gone by since I was there. My turquoise car indicator in the car seems to me moving as I drive and I am not losing connections very often (or at least not for very long), so it makes me wonder is the update rates are odd. If the time is not longer, then maybe the mileage trigger is too long. As the crow flies I had not gone far, but the road miles and time were longer. Perhaps the update rate for “unavailable” units is longer that it was in the past. I was actually hoping that it would be set for more frequent position updates, but it seems like something some of the position reports are very delayed. Lieutenant John Sprague Kitsap County Sheriff’s Office Port Orchard, WA Desk Phone: 360-337-4905 Email: jsprague@co.kitsap.wa.us ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~ 07/23/16 reported "GPS continuously dropping signal." by POPD Chuck Schandel. Asking for additional details
Note on F43: Terese Ungren: WO#37318 for another example. Also didn’t clear from my dispatches.

## Picklists
Status
Open
Closed
WAD (Closed)
SR
Testing
Awaiting Customer Sign Off
CAD Reassessment
Duplicate
Source/Group Assigned To
CENCOM
HxGN
Cloud5
MCTUser
Type
Defect
Enhancement
Training
Config
Map
Workflow
Other
App 1
CAD
NetViewer
NetDispatcher
Interface
Other
App 2
Calltaker
Dispatcher
Call/Disp
CADDBM
Informer
AniAli
ServerCommands
MDT/MPS
Other
HxGN Disposition
In Process
Delivered
Closed
Awaiting Approval
Need More Info
CAD Reassessment
MPS Reassessment
CENCOM Disposition
In Process
Testing
Closed
CAD Reassessment
Awaiting HxGN
Awaiting Cloud5
Priority
P1
P2
P3
P4
Cloud5 Disposition
In Process
Testing
Closed
CAD Reassessment
Awaiting CENCOM